## Product Backlog
SCAM REPORT — PRODUCT BACKLOG
CSC231 Agile Project Management ¦ 5 Sprints x 1 Week ¦ 20 Work Packages ¦ 158 Hours Total (excl. LOE)
WBS ID | Work Package | Phase | Priority | Est. Hrs | Sprint | Status | Responsible | Depends On | Description | Note
SPRINT 1 Week 1 — Infrastructure and Authentication Backend ¦ 28 hrs
2.1.1 | PostgreSQL + pgvector | Infrastructure | High | 7 | Sprint 1 | Done | A.P / T.P | None | Design and provision core DB schema for reports, users, statuses and announcements. Configure pgvector extension for similarity search.
2.1.2 | Prisma ORM Implementation | Infrastructure | High | 6 | Sprint 1 | Done | A.P | 2.1.1 | Define typed Prisma data models, manage schema migrations, establish query layer consumed by all backend services.
2.3.1 | Gemini LLM Integration | AI | High | 8 | Sprint 1 | Done | A.P / B.S | 2.1.1 | Connect platform to Google Gemini. Build initial prompt specification and API abstraction layer.
2.2.1 | Firebase Auth Integration | Auth | High | 7 | Sprint 1 | Done | A.P | 2.1.2 | Integrate Firebase Authentication with OAuth social login, and binary RBAC (user / admin).
Sprint 1 Sub-total |  |  |  | 28
SPRINT 2 Week 2 — Storage, RAG Pipeline and Frontend Auth ¦ 24 hrs
2.2.2 | Supabase Storage Integration | Storage | High | 7 | Sprint 2 | Done | A.P / T.P | 2.2.1 | Evidence file upload pipeline via Supabase Storage. CDN delivery configuration and bucket security policies.
2.3.2 | RAG Retrieval Logic | AI | High | 12 | Sprint 2 | Done | A.P | 2.3.1; 2.1.1 | Embedding generation pipeline. Store vector representations in pgvector. Cosine-similarity retrieval with backend latency handling.
1.1.8 | SMS smishing detectcion | backend | Medium | 5 | Sprint 2 | Done | Y.R | 2.3.2 | Passive on-device read of incoming SMS, on-device extraction of URLs and phone numbers, only the extracted identifiers are submitted to POST /check. Raw SMS body is never transmitted (PDPA, §6.3). Suspicious or Scam verdict surfaces a tap-to-review notification. | Added
1.1.9 | Call Screening | Frontend | Medium | 5 | Sprint 2 | Done | B.S | 2.3.2 | Incoming-call number checked against verified DB. Lock-screen / shade notification on match. Notification-only (Android policy). 3s budget. | Added
1.1.1 | Authentication | Frontend | High | 5 | Sprint 2 | Done | A.P | 2.2.1 | P-01 Login and P-02 Register pages. Session and token management. Prerequisite for all personalised features.
Sprint 2 Sub-total |  |  |  | 34
SPRINT 3 Week 3 — Core API, Feed and Report Detail Page ¦ 31 hrs
2.3.3 | API Services | Backend | High | 12 | Sprint 3 | To Do | ALL | 2.1.2; 2.2.1 | Full CRUD REST surface for reports, users, statuses, announcements, etc.
1.1.2 | Scam Report Feed | Frontend | Medium | 7 | Sprint 3 | Done | T.P | 1.1.1; 2.3.3 | P-03 Public Feed and P-11 My Reports. Conditional columns, status badge, and auth guard. Live statistics in public view header.
1.1.2a | Verified Report Detail | Frontend | Medium | 3 | Sprint 3 | Done | T.P | 1.1.2; 2.3.3 | P-04. Full scammer information and evidence file viewer. Shareable URL. Read-only page reached from feed or search results. | Added
1.1.6 | Data Privacy and ToS | Frontend | Low | 4 | Sprint 3 | Done | B.S | 1.1.1 | P-07 Privacy Policy and P-08 Terms of Service. Static content pages with consent checkboxes wired into registration and submission flows.
1.1.7 | Support and Settings | Frontend | Low | 5 | Sprint 3 | Done | B.S | 1.1.1 | P-12 Support / Settings. Onboarding tutorial for new users and account preferences panel.
Sprint 3 Sub-total |  |  |  | 31
SPRINT 4 Week 4 — Report Form, AI Search and Admin Queue ¦ 27 hrs
1.1.4 | Report Submission Form | Frontend | High | 8 | Sprint 4 | Done | T.P | 1.1.1; 2.2.2; 2.3.3 | P-10 Submit a Report. Validated form with evidence file upload and consent acknowledgement.
1.1.3 | AI-Powered Search UI | Frontend | High | 12 | Sprint 4 | Done | A.P / B.S | 2.3.1; 2.3.2 | P-09 AI-Powered Search. Natural-language semantic query input with ranked results from RAG engine.
1.1.10 | Share-to-app | Backend | Medium | 5 | Sprint 4 | To Do | Y.R | 2.3.3 | Share suscipicious link message, phone number, back account, etc. from another account to our application for checking | Added
1.2.1 | Pending Review Queue | Admin | Medium | 7 | Sprint 4 | Done | Y.R | 2.2.1; 2.3.3 | A-01 Pending Review Queue. Admin list of all submitted reports awaiting review. Priority flagging and sort controls.
Sprint 4 Sub-total |  |  |  | 27
SPRINT 5 Week 5 — Announcements, Admin Actions and QA/Deploy ¦ 33 hrs
1.1.5 | Announcements Feature | Frontend / Admin | Medium | 7 | Sprint 5 | Done | S.P | 2.2.1; 2.3.3 | P-05 Announcement List, P-06 Announcement Detail, and A-03 Announcement Management. Role-conditional create, edit and publish layer.
1.2.2 | Admin Action UI with AI scoring | Admin | Medium | 8 | Sprint 5 | Done | Y.R | 1.2.1 | A-02. Full case view: evidence preview, approve/reject action with remark input, status-flag escalation control, and AI scoring. | Added
3.1 | Unit and Integration Testing | Testing | High | 6 | Sprint 5 | To Do | ALL | All development packages | Unit tests for all major frontend components and backend services. Integration tests for API and database layers.
3.2 | User Acceptance Testing | Testing | Medium | 6 | Sprint 5 | To Do | ALL | 3.1 | Validation across all 15 pages against real user scenarios. Structured feedback collection and issue resolution.
3.3 | CI/CD Pipeline and Deployment | Deployment | High | 6 | Sprint 5 | To Do | T.P / S.P | 3.1 | Automated build-and-deploy pipeline. Staging environment validation. Production release with monitoring in place.
Sprint 5 Sub-total |  |  |  | 33
LEVEL-OF-EFFORT (LOE) — Ongoing throughout all sprints
4.1 | Weekly Team Sync | Project Management | LOE | Ongoing | Ongoing | LOE | ALL | — | Weekly standups and sprint retrospectives. Blocker identification and resolution.
4.2 | Progress Monitoring and Reporting | Project Management | LOE | Ongoing | Ongoing | LOE | ALL | — | Burndown chart maintenance. Status reporting to course instructor. WBS and schedule updates.
Grand Total (excl. LOE) |  |  |  | 158

## Gantt Chart
MOBILE APPLICATION PROJECT — GANTT CHART
CSC231 Agile Project Management ¦ 5 Sprints (23 Apr – 27 May) ¦ 158 Hours Total
[7 empty] | Sprint 1 — 23 Apr |  |  |  |  | Sprint 2 — 30 Apr |  |  |  |  | Sprint 3 — 7 May |  |  |  |  | Sprint 4 — 14 May |  |  |  |  | Sprint 5 — 21 May
WBS ID | Work Package | Phase | Responsible | Hrs | Sprint | Status | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27
SPRINT 1 Week 1 — Infrastructure and Authentication Backend ¦ 28 hrs
2.1.1 | PostgreSQL + pgvector | Infrastructure | A.P / T.P | 7 | Sprint 1 | Done
2.1.2 | Prisma ORM Implementation | Infrastructure | A.P | 6 | Sprint 1 | Done
2.3.1 | Gemini LLM Integration | AI | A.P / B.S | 8 | Sprint 1 | Done
2.2.1 | Firebase Auth Integration | Auth | A.P | 7 | Sprint 1 | Done
SPRINT 2 Week 2 — Storage, RAG Pipeline and Frontend Auth ¦ 24 hrs
2.2.2 | Supabase Storage Integration | Storage | A.P / T.P | 7 | Sprint 2 | Done
2.3.2 | RAG Retrieval Logic | AI | A.P | 12 | Sprint 2 | Done
1.1.1 | Authentication | Frontend | A.P | 5 | Sprint 2 | Done
1.1.8 | SMS smishing detectcion | backend | Y.R | 5 | Sprint 2 | Done
1.1.9 | Call Screening | Frontend | B.S | 5 | Sprint 2 | Done
SPRINT 3 Week 3 — Core API, Feed and Report Detail Page ¦ 31 hrs
2.3.3 | API Services | Backend | ALL | 12 | Sprint 3 | To Do
1.1.2 | Scam Report Feed | Frontend | T.P | 7 | Sprint 3 | Done
1.1.2a | Verified Report Detail | Frontend | T.P | 3 | Sprint 3 | Done
1.1.6 | Data Privacy and ToS | Frontend | B.S | 4 | Sprint 3 | Done
1.1.7 | Support and Settings | Frontend | B.S | 5 | Sprint 3 | Done
SPRINT 4 Week 4 — Report Form, AI Search and Admin Queue ¦ 27 hrs
1.1.4 | Report Submission Form | Frontend | T.P | 8 | Sprint 4 | Done
1.1.3 | AI-Powered Search UI | Frontend | A.P / B.S | 12 | Sprint 4 | Done
1.2.1 | Pending Review Queue | Admin | Y.R | 7 | Sprint 4 | Done
1.1.10 | Share-to-app | Backend | Y.R | 5 | Sprint 4 | To Do
SPRINT 5 Week 5 — Announcements, Admin Actions and QA/Deploy ¦ 33 hrs
1.1.5 | Announcements Feature | Frontend / Admin | S.P | 7 | Sprint 5 | To Do
1.2.2 | Admin Action UI with AI scoring | Admin | Y.R | 8 | Sprint 5 | To Do
3.1 | Unit and Integration Testing | Testing | ALL | 6 | Sprint 5 | To Do
3.2 | User Acceptance Testing | Testing | ALL | 6 | Sprint 5 | To Do
3.3 | CI/CD Pipeline and Deployment | Deployment | T.P / S.P | 6 | Sprint 5 | To Do
Level-of-Effort (LOE) — Ongoing throughout all sprints
4.1 | Weekly Team Sync | Project Management | ALL | Ongoing | LOE | Ongoing
4.2 | Progress Monitoring and Reporting | Project Management | ALL | Ongoing | LOE | Ongoing

## Pages Inventory
SCAM REPORT PLATFORM — PAGES INVENTORY (15 Pages)
Page sync conducted against WBS v1.3 and Wideband Delphi final consensus ¦ 2 gaps resolved ¦ WBS ID drift documented below
Page ID | Page Name | WBS ID | Access Level | Sprint | Responsible | Key Field Values | Description | Status
Public — No Login Required
P-01 | Login | 1.1.1 | Public | Sprint 2 | T.P | users.role = any | Email/password and OAuth social login entry point. | Covered
P-02 | Register | 1.1.1 | Public | Sprint 2 | T.P | — | Sign-up form with consent acknowledgement checkbox. | Covered
P-03 | Home / Public Feed | 1.1.2 | Public | Sprint 3 | T.P | reports.status = verified | Live statistics, list of verified scam reports with filters and sort controls. | Covered
P-04 | Verified Report Detail | 1.1.2a | Public | Sprint 3 | T.P | reports.status = verified | Full scammer information and evidence files. Shareable URL. Reached from feed or search. | Added
P-05 | Announcements List | 1.1.5 | Public | Sprint 5 | S.P | announcements.category | List of published announcements with category filter. | Covered
P-06 | Announcement Detail | 1.1.5 | Public | Sprint 5 | S.P | announcements.category | Full content of a single announcement. Read-only. | Covered
P-07 | Privacy Policy | 1.1.6 | Public | Sprint 3 | B.S | — | Static data privacy policy page. | Covered
P-08 | Terms of Service | 1.1.6 | Public | Sprint 3 | B.S | — | Static Terms of Service page linked from registration and submission consent. | Covered
Authenticated — Login Required
P-09 | AI-Powered Search | 1.1.3 | Auth Required | Sprint 4 | A.P / B.S | — | Semantic query input with ranked results from RAG engine. | Covered
P-10 | Submit a Report | 1.1.4 | Auth Required | Sprint 4 | T.P | reports.status = pending | Validated form with evidence file upload and consent checkbox. | Covered
P-11 | My Reports | 1.1.2 | Auth Required | Sprint 3 | T.P | reports.status: pending / under_review / verified / rejected | User's own reports with status badges and case detail view. | Covered
P-12 | Support / Settings | 1.1.7 | Auth Required | Sprint 3 | B.S | — | Onboarding tutorial, account preferences, and settings panel. | Covered
Admin Only
A-01 | Pending Review Queue | 1.2.1 | Admin Only | Sprint 4 | Y.R | reports.priority: low / medium / high | All submitted reports awaiting review. Priority flagging and sort controls. | Covered
A-02 | Report Review Detail | 1.2.2 | Admin Only | Sprint 5 | Y.R | review_actions.action: assigned / under_review / approved / rejected / escalated | Full case view: evidence preview, approve/reject with remark, escalation control. | Scoped
A-03 | Announcement Management | 1.1.5 | Admin Only | Sprint 5 | S.P | announcements.category: activities / fraud_prevention | Create, edit, publish/unpublish, and delete announcements. Category and tag assignment. | Covered
WBS ID Drift Reference — Original WBS IDs vs Delphi-Revised IDs
Original WBS ID | Work Package | [5 empty] | Change Note
1.1.3 (original) | My Reports | [5 empty] | Absorbed into 1.1.2 Scam Report Feed after Delphi merge
1.1.5 (original) | Report Submission | [5 empty] | Renumbered to 1.1.4 after Delphi merge
1.1.6 (original) | Announcements | [5 empty] | Renumbered to 1.1.5 after Delphi merge
1.1.8 (original) | Support and Settings | [5 empty] | Renumbered to 1.1.7 after Delphi merge
1.2.3 (original) | Announcement Mgmt | [5 empty] | Merged into 1.1.5 Announcements Feature
1.1.2a (new) | Verified Report Detail | [5 empty] | Added to address P-04 gap identified in page sync
Database Field Values Reference
Field | Allowed Values | [5 empty] | Usage Notes
users.role | user, admin | [5 empty] | Binary RBAC. All protected routes gate access on this value.
reports.status | pending, under_review, verified, rejected | [5 empty] | Controlled by admin review actions. Displayed as status badge in P-03, P-11, A-01, A-02.
reports.priority | low, medium, high | [5 empty] | Used in A-01 sort and flag controls and surfaced in A-02 case header.
review_actions.action | assigned, under_review, approved, rejected, escalated | [5 empty] | Full audit trail of admin decisions. Drives escalation control in A-02.
announcements.category | activities, fraud_prevention | [5 empty] | Category filter in P-05. Assigned during creation or editing in A-03.

## Sprint Summary
SCAM REPORT PLATFORM — SPRINT SUMMARY
CSC231 Agile PM ¦ 5 Sprints x 1 Week ¦ 158 hrs total ¦ Estimates from Wideband Delphi (2 rounds)
Sprint | Focus Area | Timeline | Work Packages | Hrs | % of Total | Team Members
Sprint 1 | Infrastructure and Authentication Backend | Week 1 | 2.1.1, 2.1.2, 2.3.1, 2.2.1 | 28 | 19.58% | A.P (Lead), T.P, B.S
Sprint 2 | Storage, RAG Pipeline and Frontend Auth | Week 2 | 2.2.2, 2.3.2, 1.1.1,1.1.14,1.1.15 | 34 | 23.78% | A.P (Lead), T.P, B.S, Y.R
Sprint 3 | Core API, Feed and Report Detail Page | Week 3 | 2.3.3, 1.1.2, 1.1.2a, 1.1.6, 1.1.7 | 31 | 21.68% | All Members
Sprint 4 | Report Form, AI Search and Admin Queue | Week 4 | 1.1.4, 1.1.3, 1.2.1,1.1.16 | 32 | 22.38% | A.P, T.P, Y.R, B.S
Sprint 5 | Announcements, Admin Actions and QA/Deploy | Week 5 | 1.1.5, 1.2.2, 3.1, 3.2, 3.3 | 33 | 23.08% | All Members
Total (excl. LOE) |  |  |  | 158 | 100%
Version note: v1 total = 140 hrs (Wideband Delphi consensus). v2 total = 143 hrs after adding WBS 1.1.2a Verified Report Detail (+3 hrs) identified during page sync.
Delphi convergence: 2 rounds required. Grand mean Round 1: 128.6 hrs. Round 2: 132.2 hrs. Range reduced from 15 hrs to 12 hrs (-20%). Std deviation reduced from 5.31 hrs to 4.15 hrs (-22%).