## Wideband Delphi Estimation
SCAM REPORT PLATFORM — Wideband Delphi Estimation
WBS ID | Work Package | Round 1 — Independent Estimation (hrs) | [5 empty] | Round 2 — Revised Estimation (hrs) | [5 empty] | Consensus Hrs | Phase | Responsible
|  | A.P. | T.P. | S.P. | B.S. | Y.R. | Mean | A.P. | T.P. | S.P. | B.S. | Y.R. | Mean
1.1.1 | Authentication | 5 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Frontend | A.P.
1.1.2 | Scam Report Feed | 7 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 6 | 7 | 6 | 6.4 | 7 | Frontend | T.P.
1.1.2a | Verified Report Detail | 1 | 2 | 3 | 2 | 3 | 2.2 | 2 | 2 | 3 | 3 | 3 | 2.6 | 3 | Frontend | B.S.
1.1.3 | AI-Powered Search UI | 13 | 15 | 14 | 10 | 14 | 13.2 | 11 | 12 | 12 | 12 | 12 | 11.8 | 12 | Frontend | A.P. / B.S.
1.1.4 | Report Submission Form | 7 | 10 | 8 | 9 | 5 | 7.8 | 7 | 9 | 8 | 8 | 8 | 8 | 8 | Frontend | T.P.
1.1.5 | Announcements Feature | 7 | 8 | 8 | 5 | 5 | 6.6 | 7 | 7 | 7 | 6 | 7 | 6.8 | 7 | Frontend/Admin | S.P.
1.1.6 | Data Privacy & ToS | 5 | 6 | 4 | 3 | 5 | 4.6 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | Frontend | B.S.
1.1.7 | Support & Settings | 3 | 5 | 4 | 8 | 4 | 4.8 | 5 | 4 | 4 | 5 | 4 | 4.4 | 5 | Frontend | B.S.
1.1.8 | SMS smishing detectcion | 4 | 5 | 3 | 4 | 5 | 4.2 | 5 | 5 | 4 | 5 | 5 | 4.8 | 5 | Backend | Y.R
1.1.9 | Call Screening | 5 | 6 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4.8 | 5 | Frontend | B.S.
1.1.10 | Share-to-app | 6 | 6 | 5 | 4 | 5 | 5.2 | 4 | 5 | 4 | 4 | 5 | 4.4 | 5 | Backend | Y.R.
1.2.1 | Pending Review Queue | 7 | 6 | 6 | 6 | 6 | 6.2 | 7 | 6 | 7 | 8 | 7 | 7 | 7 | Admin | Y.R.
1.2.2 | Admin Action UI with AI scoring | 7 | 7 | 8 | 8 | 3 | 6.6 | 7 | 7 | 7 | 8 | 7 | 7.2 | 8 | Admin | Y.R.
2.1.1 | PostgreSQL + pgvector | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 6.8 | 7 | Infrastructure | A.P. / T.P.
2.1.2 | Prisma ORM Implementation | 5 | 5 | 6 | 5 | 3 | 4.8 | 5 | 5 | 6 | 6 | 6 | 5.6 | 6 | Infrastructure | A.P.
2.2.1 | Firebase Auth Integration | 5 | 5 | 5 | 4 | 5 | 4.8 | 5 | 5 | 5 | 10 | 6 | 6.2 | 7 | Auth | A.P.
2.2.2 | Supabase Storage Integration | 5 | 5 | 5 | 7 | 5 | 5.4 | 5 | 5 | 6 | 12 | 6 | 6.8 | 7 | Storage | A.P. / T.P.
2.3.1 | Gemini LLM Integration | 5 | 7 | 5 | 4 | 6 | 5.4 | 7 | 7 | 7 | 8 | 7 | 7.2 | 8 | AI | A.P. / B.S.
2.3.2 | RAG Retrieval Logic | 11 | 12 | 12 | 11 | 12 | 11.6 | 13 | 12 | 12 | 7 | 12 | 11.2 | 12 | AI | A.P.
2.3.3 | API Services | 13 | 12 | 13 | 12 | 12 | 12.4 | 11 | 12 | 12 | 11 | 12 | 11.6 | 12 | Backend | All Members
3.1 | Unit & Integration Testing | 7 | 6 | 7 | 6 | 7 | 6.6 | 5 | 6 | 6 | 6 | 5 | 5.6 | 6 | Testing | All Members
3.2 | User Acceptance Testing | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 5.2 | 6 | Testing | All Members
3.3 | CI/CD Pipeline & Deployment | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 5.2 | 6 | Deployment | T.P. / S.P.
TOTAL |  | 145 | 154 | 150 | 140 | 138 | 145.4 | 144 | 146 | 147 | 157 | 149 | 148.6 | 158